## Sheet1
Sr. No. | Functionality List | Status
1 | Weapons needs to added | Pending
2 | Enemy needs to be added | Done
3 | Rock obstacle collider | Done
4 | More Enemy needs to be added | Done
5 | Navigation | Done
6 | Canavas UI Design | Partially Done
7 | Help Instruction | Pending
8 | Game timer for different Levels | Done
9 | Level 1 Testing | Done
10 | Level 2 Testing | In- Progress
11 | Level 3 Testing | In- Progress

## Level 1 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Developer Name
TC_1 | Level 1 > After pressing space button | It should attack or move forward | Character stops at one point and doesn’t move further once pressed spacebar key
TC_2 | Level 1> Character movement | Character movement should be little faster | Character is moving with low speed
TC_3 | Level 1> Minimap | Minimap should show in Level 1 | Minimap is not showing under Level 1
TC_4 | Level 1 > Enemy collider | Enemy collider should work with character | Enemey collider is not working
TC_5 | Level 1> Weapon | Weapons needs to be added | Weapons needs to be added

## Level 2 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Developer Name
TC_1 | Level 2> Weapon | Weapons needs to be added | Weapons needs to be added
TC_2 | Level 2 > Enemy collider | Enemy collider should work with character | Enemey collider is not working

## Level 3 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Developer Name
TC_1 | Level 3 > Weapon | Weapons needs to be added | Weapons needs to be added
TC_2 | Level 3 > Enemy collider | Enemy collider should work with character | Enemey collider is not working